## Slide 1: Production Model Update Schedule

## Slide 2: Example Calendar Showing Key Dates

## Slide 3: TWO Updates of the Production Model per Month
1st Update – Before 2nd Tuesday
2nd Update – Before Last Tuesday

## Slide 4: 1st Update
  To be completed before the 2nd Tuesday of Every Month

## Slide 5: Step 1 Load Actuals From Prior Month
  Mine Engineer Loads Actuals into Production Model

## Slide 6: An Example of An EOM Production Report That Contains the Actual Information per Section Needed For the Production Model

## Slide 7: Enter Actuals From EOM Into Production Model
4 Tabs to Enter Assumptions
Monthly Assumptions Are Overwritten by Actuals From the End of the Month Production Report

## Slide 8: Step 2 Update End of Month Face Locations in Forecaster
  The Mine Engineer Runs the Most Recent mdb Forecaster File With the Updated End of the Month Face Locations and Then Links the mdb File to the Production Model.
IF THE MINE ENGINEER IS USING THE FORECASTER PROGRAM PLEASE COMPLETE THIS STEP BEFORE REVIEWING THE PRODUCTION MODEL D2 REPORT

## Slide 9: Update End of Month Face Locations in Forecaster
Update the Date for Each Active Section
Update the Section Plus for Each Active Section

## Slide 10: Link Forecaster Database to Production Model
Database Linked to Download Tab
1. Select Data
2. Select Connections
3. Select Properties
4. Insert the Path to the mdb File in 4 Locations

## Slide 11: Step 3 Review Assumptions and Verify D2 Output is Correct
  2 Options Possible
  The Mine Engineer Reviews the Production Model Assumptions and D2 Sheets to Verify the Assumptions and Determines the Assumptions Should Remain the Same Going Forward.
  The Review Reveals a Change to the Assumptions is Necessary.

## Slide 12: Review D2 Output From Production Model
11 D2 Report Tabs
Select Yellow Cell to Pick Month to Start Each Tab of D2 Report
Information Is Pulled From the Mining Summary Tab and Can be Printed to Review
After Review, Adjustments Can be Made to Assumptions Either in the Forecaster if Used or on the Longwall, Mains, Gates, or Panels Tabs. The Updates Move Through to the D2 Report

## Slide 13: Option 1) Review Checks Out and Everything is Acceptable
  After Verifying the Acceptability of the Production Model D2 Output With the Superintendent and/or VP:
  Go to Step 4 – to Submit Update

## Slide 14: Option 2) Review Reveals a Change to the Assumptions is Necessary
  The Mine Engineer Should:
    Discuss the Findings of the Review With the Superintendent.
    Determine, with the Superintendent, How to Adjust the Assumptions to Better Forecast What is Occurring.
  Then The Mine Engineer Should:
    Make Adjustments to the Assumptions.
    Take a Look at the New Output.
    Inform the Superintendent and/or VP of the Changes Made and Differences Resulting From Those Changes in the D2 Output.

## Slide 15: Step 4 Submit The 1st Update
  After Verifying the Acceptability of the Production Model D2 Output With the Superintendent and/or VP:
    The Mine Engineer Should Copy the Reviewed File and Any Linked Updated Forecaster mdb File and Quality mdb File to the Assigned Folder on the P Drive.
    After Copying the Mine Engineer Should Send an Email Notification to Capital Planning Before the 2nd Tuesday of Every Month.

## Slide 16: 2nd Update
  To be completed before the Last Tuesday of Every Month

## Slide 17: Step 5 Update Face Locations in Forecaster
  The Mine Engineer Runs the Most Recent mdb Forecaster File With Updated Face Locations as of Monday 12:01AM (Monday the day Before the Last Tuesday of the Month) and Then Links the mdb File to the Production Model.
IF THE MINE ENGINEER IS USING THE FORECASTER PROGRAM PLEASE COMPLETE THIS STEP BEFORE REVIEWING THE PRODUCTION MODEL D2 REPORT

## Slide 18: Step 6 Review Assumptions and Verify D2 Output is Correct
  2 Options Possible
  The Mine Engineer Reviews the Production Model Assumptions and D2 Sheets to Verify the Assumptions and Determines the Assumptions Should Remain the Same Going Forward.
  The Review Reveals a Change to the Assumptions is Necessary.

## Slide 19: Review D2 Output From Production Model
11 D2 Report Tabs
Select Yellow Cell to Pick Month to Start Each Tab of D2 Report
Information Is Pulled From the Mining Summary Tab and Can be Printed to Review
After Review, Adjustments Can be Made to Assumptions Either in the Forecaster if Used or on the Longwall, Mains, Gates, or Panels Tabs. The Updates Move Through to the D2 Report

## Slide 20: Option 1) Review Checks Out and Everything is Acceptable
  After Verifying the Acceptability of the Production Model D2 Output With the Superintendent and/or VP:
  Go to Step 7 – to Submit Update

## Slide 21: Option 2) Review Reveals a Change to the Assumptions is Necessary
  The Mine Engineer Should:
    Discuss the Findings of the Review With the Superintendent.
    Determine, with the Superintendent, How to Adjust the Assumptions to Better Forecast What is Occurring.
  Then The Mine Engineer Should:
    Make Adjustments to the Assumptions.
    Take a Look at the New Output.
    Inform the Superintendent and/or VP of the Changes Made and Differences Resulting From Those Changes in the D2 Output.

## Slide 22: Step 7 Submit The 2nd Update
  After Verifying the Acceptability of the Production Model D2 Output With the Superintendent and/or VP:
    The Mine Engineer Should Copy the Reviewed File and Any Linked Updated Forecaster mdb File and Quality mdb File to the Assigned Folder on the P Drive.
    After Copying the Mine Engineer Should Send an Email Notification to Capital Planning Before the Last Tuesday of Every Month.